## Sheet1
Status | ECD | ID |  |  | DESCRIPTION OF TASK |  |  | Person
INPRG |  | 1 |  |  | Convert to single persisent pre-initialized datasource
COMP |  |  | 1 |  |  | Convert Data Structures |  | Brighid
|  |  |  | 1 |  |  | Node Data
|  |  |  | 2 |  |  | Profile Data
COMP |  |  | 2 |  |  | Convert GameController |  | Brighid
|  |  |  | 1 |  |  | Read Data
|  |  |  | 2 |  |  | Store Data
|  |  |  | 3 |  |  | Update Data
COMP |  |  | 3 |  |  | Rebuild Renderer |  | Brighid
|  |  |  | 1 |  |  | Node Grid
|  |  |  | 2 |  |  | Node Display
|  |  |  | 3 |  |  | Update Scene
INPRG | 2018-03-04 |  | 4 |  |  | Rebuild Player Profile Display |  | Yong
|  |  |  | 1 |  |  | Reattach display canvas
INPRG | ? |  | 5 |  |  | Reattach Drills & Minigames |  | Andrew
|  |  |  | 1 |  |  | Refer to correct handles in GameController
COMP |  |  | 6 |  |  | Document new systems |  | Brighid
|  |  |  | 1 |  |  | GameController
|  |  |  | 2 |  |  | Renderer
|  |  |  | 3 |  |  | Listeners
|  |  |  | 4 |  |  | Profile Display
INPRG |  | 2 |  |  | Optimize Game Settings & Logic |  |  | Team
INPRG | ? |  | 1 |  |  | Identify settings & logic of interest
|  |  | 2 |  |  | Test play with settings to identify improvement areas
|  |  | 3 |  |  | Document improvements
INPRG | ? | 3 |  |  | Build Test System |  |  | Brighid
INPRG | ? | 4 |  |  | Player Score System |  |  | Brighid
|  |  | 1 |  |  | Score system
|  |  | 2 |  |  | Display Score
|  |  | 3 |  |  | Initialize minimum system requirements
|  | 5 |  |  | Aesthetics of gameplay
Connecting Lines
todo